## Deliverables
Date | Column1 | Column2 | Column3 | Column4 | Column5 | Column6
| TL1 | TL2 | TL3 | TL4 | TL5 | TL6
2025-02-25
2025-02-27
2025-02-25 |  | 2025-02-25

## Budget
Cost Analysis
SN | Member Name | Role | Estimated Hours | Hourly Rate ($) | Estimated Cost ($) | Actual Hours | Total Cost ($) | Variance | Comments
1 | Shruti Debnath | IT Manager | 55 | 16 | 880
2 | Pratik Rauniyar | Software Architect | 60 | 18 | 1080
3 | Dristanta Silwal | Software Architect | 65 | 18 | 1170
4 | Kushal Khadka | QA Manager | 40 | 16 | 640
5 | Sikha Chaudary | Project Manager | 30 | 20 | 600
6 | Pramil Shrestha | AI Specialist | 35 | 17 | 595
7 | Prabesh Tamang | Version Control Manager | 40 | 17 | 680
| Total |  | 325 |  | 5645

## Gantt
Status Color
Completed
Working Currently
Planned
SN | Feature Breakdown | Estimated Time (weeks) | Prereq | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
Shruti Debnath
1 | Rough UI Design | 1 | N/A | Completed
2 | Gathering assests | 1 | N/A | Completed
3 | Main Menu (game-lobby, ShopScene) design | 2 | 1,2 | Completed
4 | Scripts writting | 2 | 3 | Completed
5 | New Buttons & Button Update | 1 | 2,3 | Working Currently
6 | Adding tracking bars on the Game screen | 2 | 2,3 | Working Currently
7 | Game End Scene | 2 | 6 | Planned
8 | Final Touch UP | 1 | 5,6,7 | Planned
9 | Testing and Debugging | 1 | 8 | Planned
10 | Documentation | 1 | 9 | Planned
Pratik Rauniyar
1 | Player development | 1 | N/A | Completed
2 | Actions(Player) | 1 | 1 | Working Currently
3 | Game Mechanics(logic and development) | 2 | 2 | Working Currently
4 | Game plots | 2 | 3 | Working Currently
5 | logic for game win/loose | 1 | 2, 3 | Planned
6 | logic for player and enemy reposne | 2 | 3, 4 | Planned
7 | Testing and debugging | 1 | 6 | Planned
8 | Documentation | 1 | 7 | Planned
Dristanta Silwal
1 | AI state machine Design | 2 | N/A | Completed
2 | Enemy attribute randomization | 1 | 1 | Working Currently
3 | Difficulty adjustment logic | 2 | 2 | Working Currently
4 | Enemy behavior programming | 4 | 1 | Planned
5 | Defeat and cleanup logic | 2 | 3, 4 | Planned
6 | Animation | 2 | 5 | Planned
7 | Testing and debugging | 1 | 6 | Planned
8 | Documentation | 1 | 7 | Planned
Kushal Khada
1 | Attack Enemy | 1 | N/A | Working Currently
2 | Pick up weapon | 1 | 1 | Working Currently
3 | Activates special power | 2 | 2 | Planned
4 | Takes Damages | 1 | 2 | Planned
5 | Knocked out | 1 | 3 | Planned
6 | Documentation | 1 | 4 | Planned
Sikha Chaudhary
1 | collectables placed(treasure) | 1 | N/A | Completed
2 | collectables to be placed(gems, poison) | 1 | 1 | Working Currently
3 | collectables hide/show logic | 1 | 2 | Planned
4 | collectables animation | 2 | 3 | Planned
5 | Testing and debugging | 1 | 4 | Planned
6 | Documentation | 1 | 5 | Planned
Pramil Shrestha
1 | Enter Lobby | 1 | N/A | Working Currently
2 | Manage Coins | 1 | 1 | Working Currently
3 | View Inventory | 1 | 2 | Planned
4 | Select Characters | 2 | 3 | Planned
5 | Equip Weapons | 1 | 4 | Planned
6 | Documentation | 1 | 5 | Planned
Prabesh Tamang
1 | Background stort concept development | 1 | N/A | Completed
2 | Story refinement and integration | 2 | 1 | Completed
3 | Story Testing and feedback | 1 | 1 | Completed
4 | Final Story Implementation | 1 | 2 | Completed
5 | Audio Assets Collection | 1 | 3 | Working Currently
6 | Music and Sound Design | 2 | 4 | Working Currently
7 | Sound Integration and testing | 2 | 5 | Planned
8 | Final Sounds Adjustments | 1 | 6 | Planned
9 | Bug Fixing and optimization | 1 | 7 | Planned

## estimated schedule
Schedule Work
SN | Name | Task Description | Estimated Hours | Actual Hours | Status | Comments
1 | Jaskaran Singh | Rough UI Design | 1 | N/A | Planned
2 | Jaskaran Singh | Gathering Assets | 1 | N/A | Planned
3 | Jaskaran Singh | Main Menu (game-lobby, ShopScene) Design | 2 | N/A | Planned
4 | Jaskaran Singh | Scripts Writing | 2 | N/A | Planned
5 | Jaskaran Singh | New Buttons & Button Update | 1 | N/A | Planned | Implementing new UI features
6 | Jaskaran Singh | Adding Tracking Bars on Game Screen | 2 | N/A | Planned | In progress, needs completion
7 | Jaskaran Singh | Game End Scene | 2 | N/A | Planned | Scheduled for next phase
8 | Jaskaran Singh | Final Touch Up | 1 | N/A | Planned | Scheduled after all features complete
9 | Jaskaran Singh | Testing and Debugging | 1 | N/A | Planned | After final touch-up
10 | Jaskaran Singh | Documentation | 1 | N/A | Planned | Pending completion of features
11 | Safal Shrestha | Player Development | 1 | 1 | Completed
12 | Safal Shrestha | Actions (Player) | 1 | N/A | Working Currently | Implementing player actions
13 | Safal Shrestha | Game Mechanics (logic and development) | 2 | N/A | Working Currently | In progress
14 | Safal Shrestha | Attack Enemy | 1 | N/A | Working Currently | Implementing enemy attack logic
15 | Safal Shrestha | Pick Up Weapon | 1 | N/A | Planned
16 | Safal Shrestha | Activates Special Power | 2 | N/A | Planned | Scheduled after current tasks
17 | Safal Shrestha | Takes Damage | 1 | N/A | Planned | Scheduled after attack implementation
18 | Safal Shrestha | Knocked Out | 1 | N/A | Planned | Scheduled after taking damage logic
19 | Syed | Enemy Placement | 1 | 1 | Completed
20 | Syed | Enemy Attribute Randomization | 1 | N/A | Working Currently | In progress
21 | Syed | Difficulty Adjustment Logic | 2 | N/A | Working Currently | In progress
22 | Syed | Enemy Behavior Programming | 4 | N/A | Planned | Scheduled for next phase
23 | Syed | Defeat and Cleanup Logic | 2 | N/A | Planned | Scheduled after behavior programming
24 | Syed | Animation | 2 | N/A | Planned | Scheduled after other tasks
27 | Syed | Testing and Debugging | 1 | N/A | Planned | After completion of enemy behavior
27 | Syed | Documentation | 1 | N/A | Planned | Pending completion of tasks
33 | Ayden | Collectables Placed (treasure) | 1 | N/A | Planned
34 | Ayden | Sprites
35 | Ayden | Collectables to be Placed (gems, poison)
36 | Ayden | Collectables Hide/Show Logic
37 | Ayden | Collectables Animation
38 | Ayden | Testing and Debugging
39 | Ayden | Documentation
40 | Gurneet
41 | Gurneet
42 | Gurneet
43 | Gurneet
44 | Gurneet
45 | Gurneet
46 | Ro | Bacic Level Desing | 1 | 1 | Completed
47 | Ro
48 | Ro
49 | Ro
50 | Ro
51 | Ro
52 | Ro
53 | Ro
53 | Ro