## Gantt
Status Color
Completed
Working Currently
Planned
SN | Feature Breakdown | Estimated Time (weeks) | Prereq | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
Jaskaran
1 | Rough UI Design | 1 | N/A | Planned
2 | Main Menu (game-lobby, ShopScene) design |  |  | Planned
3 |  |  |  | Planned
4 |  |  |  | Planned
5 |  |  |  | Planned
6 |  |  |  | Planned
7 |  |  |  | Planned
8 |  |  |  | Planned
9 | Testing and Debugging |  |  | Planned
10 | Documentation |  |  | Planned
Safal
1 | Player development | 1 | N/A | Completed | bar: Week 1
2 | Actions(Player) | 1 | 1 | Working Currently | bar: Week 2
3 | Game Mechanics(logic and development) | 2 | 2 | Working Currently | bar: Week 3 to Week 4
4 | Attack Enemy | 2 | 3 | Working Currently | bar: Week 5 to Week 6
5 | logic for game win/loose | 1 | 2, 3 | Planned | bar: Week 7
6 | logic for player and enemy reposne | 2 | 3, 4 | Planned | bar: Week 8 to Week 9
7 | Pick up weapon | 1 | 1 | Planned
8 | Activates special power
9 | Testing and debugging | 1 | 6 | Planned | bar: Week 10
10 | Documentation | 1 | 7 | Planned | bar: Week 11
Syed
1 | Enemy Placement | 2 | N/A | Completed | bar: Week 1
2 |  |  |  | Planned
3 |  |  |  | Planned
4 |  |  |  | Planned
5 |  |  |  | Planned
6 |  |  |  | Planned
7 |  |  |  | Planned
8 |  |  |  | Planned
Ayden
1 | collectables placed | 1 | N/A | Planned | bar: Week 1
2 | collectables to be placed |  |  | Planned | bar: Week 2
3 |  |  |  | Planned | bar: Week 3
4 |  |  |  | Planned | bar: Week 4 to Week 5
5 |  |  |  | Planned | bar: Week 6
6 |  |  |  | Planned | bar: Week 7
Ro
1 | Enter Lobby | 1 | N/A | Working Currently
2 | Level Floors |  |  | Working Currently
3 |  |  |  | Planned
4 |  |  |  | Planned
5 |  |  |  | Planned
6 | Documentation | 1 | 5 | Planned
Gurneet
1 | Music and Sound Design |  |  | Completed
2 |  |  |  | Planned
3 |  |  |  | Planned
4 |  |  |  | Planned
5 |  |  |  | Planned
6 |  |  |  | Planned
7 |  |  |  | Planned
8 |  |  |  | Planned
9 |  |  |  | Planned

## estimated schedule
Schedule Work
SN | Name | Task Description | Estimated Hours | Actual Hours | Status | Comments
1 | Jaskaran Singh | Rough UI Design | 1 | N/A | Planned
2 | Jaskaran Singh |  |  | N/A | Planned
3 | Jaskaran Singh | Main Menu (game-lobby, ShopScene) Design |  | N/A | Planned
4 | Jaskaran Singh |  |  | N/A | Planned
5 | Jaskaran Singh |  |  | N/A | Planned
6 | Jaskaran Singh |  |  | N/A | Planned
7 | Jaskaran Singh |  |  | N/A | Planned
8 | Jaskaran Singh |  |  | N/A | Planned
9 | Jaskaran Singh | Testing and Debugging |  | N/A | Planned
10 | Jaskaran Singh | Documentation |  | N/A | Planned
11 | Safal Shrestha | Player Development | 1 | 1 | Completed
12 | Safal Shrestha | Actions (Player) | 1 | N/A | Working Currently | Implementing player actions
13 | Safal Shrestha | Game Mechanics (logic and development) | 2 | N/A | Working Currently | In progress
14 | Safal Shrestha | Attack Enemy | 1 | N/A | Working Currently | Implementing enemy attack logic
15 | Safal Shrestha | Pick Up Weapon | 1 | N/A | Planned
16 | Safal Shrestha | Activates Special Power | 2 | N/A | Planned | Scheduled after current tasks
17 | Safal Shrestha | Takes Damage | 1 | N/A | Planned | Scheduled after attack implementation
18 | Safal Shrestha | Knocked Out | 1 | N/A | Planned | Scheduled after taking damage logic
19 | Syed | Enemy Placement | 1 | N/A | Completed
20 | Syed | Enemy Attribute Randomization |  | N/A | Working Currently
21 | Syed |  |  | N/A | Working Currently
22 | Syed |  |  | N/A | Planned
23 | Syed |  |  | N/A | Planned
24 | Syed |  |  | N/A | Planned
27 | Syed | Testing and Debugging |  | N/A | Planned
27 | Syed | Documentation |  | N/A | Planned
33 | Ayden | Collectables Placed (treasure) | 1 | N/A | Planned
34 | Ayden | Sprites
35 | Ayden
36 | Ayden
37 | Ayden
38 | Ayden
39 | Ayden | Documentation
40 | Gurneet
41 | Gurneet
42 | Gurneet
43 | Gurneet
44 | Gurneet
45 | Gurneet
46 | Ro | Bacic Level Desing | 1 | 1 | Completed
47 | Ro
48 | Ro
49 | Ro
50 | Ro
51 | Ro
52 | Ro
53 | Ro
53 | Ro