## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Anne | 10100 | 6800 | 3300 | 5000 | 800 | 4200 | 1000 | 2100 | -1100 | 1100 | 1300 | -200 | 3000 | 2600 | 400
Bill | 5100 | 4000 | 1100 | 0 | 0 | 0 | 1000 | 900 | 100 | 1100 | 1000 | 100 | 3000 | 2100 | 900
Chris | 5100 | 6900 | -1800 | 0 | 0 | 0 | 1000 | 1100 | -100 | 1100 | 1500 | -400 | 3000 | 4300 | -1300
Dan | 5100 | 7900 | -2800 | 0 | 1800 | -1800 | 1000 | 1500 | -500 | 1100 | 1100 | 0 | 3000 | 3500 | -500
Eric | 6400 | 5900 | 500 | 1300 | 600 | 700 | 1000 | 900 | 100 | 1100 | 900 | 200 | 3000 | 3500 | -500
Fran | 8500 | 9000 | -500 | 3400 | 3300 | 100 | 1000 | 900 | 100 | 1100 | 1300 | -200 | 3000 | 3500 | -500
Total | 40300 | 40500 | -200 | 9700 | 6500 | 3200 | 6000 | 7400 | -1400 | 6600 | 7100 | -500 | 18000 | 19500 | -1500

## Gantt
S.N. |  | predicted time(hrs) | time spent(hrs) | Precedent | Status | key | complete | this week | planned
| Aiden |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
1 | Player Idle Sprites | 4 | 3 | N/A | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete
2 | Player Movement Sprites | 5 | 5 | 1 | complete | planned 5: complete; planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete
3 | Player Combat Sprites | 7 |  | 1 | this week | planned 10: this week; planned 11: this week; planned 12: this week; planned 13: this week; planned 14: this week
4 | Health Pickups | 4 |  | N/A | this week | planned 15: this week
5 | Weapons | 10 |  | N/A | planned | planned 16: planned; planned 17: planned; planned 18: planned
6 | Enemy Movement Sprites | 5 |  | N/A | planned | planned 19: planned; planned 20: planned; planned 21: planned
7 | Enemy Combat Sprites | 6 |  | 6 | planned | planned 22: planned; planned 23: planned; planned 24: planned; planned 25: planned
8 | Boss Sprites | 4 |  | N/A | planned | planned 26: planned; planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned; planned 31: planned; planned 32: planned; planned 33: planned; planned 34: planned; planned 35: planned; planned 36: planned; planned 37: planned; planned 38: planned
9 | Boss Combat Sprites | 5 |  | 8 | planned | planned 39: planned
| totals | 50 | 8
Ro
1 |  |  |  |  | planned
2 |  |  |  |  | planned
3 |  |  |  |  | planned
4 |  |  |  |  | planned
| totals | 0 | 0
Jaskaran
1 |  |  |  |  | planned
2 |  |  |  |  | planned
3 |  |  |  |  | planned
| totals | 0 | 0
Safal
1 | Player development | 4 | 3 | N/A | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete
2 | Actions(Player) | 3 | 3 | 1 | complete | planned 5: complete; planned 6: complete; planned 7: complete
3 | Game Mechanics(logic and development) | 8 | 9 | 2 | complete | planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete
4 | Attack Enemy | 4 | 3 | 3 | complete | planned 16: complete; planned 17: complete; planned 18: complete; planned 19: complete
5 | logic for game win/loose | 6 |  | 2, 3 | this week | planned 16: this week; planned 17: this week; planned 18: this week; planned 19: this week; planned 20: this week; planned 21: this week
6 | logic for player and enemy reposne | 4 |  | 3, 4 | this week | planned 20: this week; planned 21: this week; planned 22: this week; planned 23: this week
7 | Pick up weapon | 5 |  | 4 | planned | planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned; planned 24: planned
8 | Activates special power | 6 |  | 5 | planned | planned 25: planned; planned 26: planned; planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned
9 | Testing and debugging | 5 |  | 8 | planned | planned 31: planned; planned 32: planned; planned 33: planned; planned 34: planned; planned 35: planned; planned 36: planned
10 | Documentation | 2 |  | 9 | planned | planned 37: planned; planned 38: planned
11 | Integrate With Other Components | 4 |  | 8 | planned | planned 39: planned; planned 40: planned; planned 41: planned; planned 42: planned
| totals | 51 | 18
Syed
1 | Enemy Placement | 2 | 3 |  | complete | key 1: complete; complete 2: complete
2 | Enemy Movement | 2 | 3 |  | complete | bar: this week 3 to planned 4
3 | Enemy Attack Pattern | 4 |  |  | this week | bar: planned 5 to planned 8
4 | Enemy Design | 3 |  |  | this week | bar: planned 9 to planned 11
5 | Boss Enemy Placement | 2 |  |  | planned
6 | Boss Enemy Movement |  |  |  | planned
7 | Boss Enemy Attack Pattern |  |  |  | planned
8 | Boss Enemy and Level Design |  |  |  | planned
9 | Testing and Debugging |  |  |  | planned
10 | Demo Mode |  |  |  | planned
11 | Documentation |  |  |  | planned
| totals | 13 | 6
Gurneet
1 | Collect Assets | 4 | 4 |  | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
2 | Set Background Music | 3 | 5 |  | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
3 | Build Mixer | 8 | 12 |  | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
4 | Integrate with events | 8 | 12 |  | complete | planned 17: complete; planned 18: complete
5 | Testing and debugging | 6 |  |  | this week | planned 19: this week; planned 20: this week; planned 21: this week; planned 22: this week; planned 23: this week; planned 24: this week
6 | Final Mix &Adjustments | 3 |  |  | this week | planned 25: this week; planned 26: this week
7 | Debug & Documentation | 2 |  |  | planned | planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned
| totals | 34 | 33
| group totals (hrs) | 101 | 26
| group totals ($) | 10100 | 2600

## Team Mate Delverables
TL 1 Deliverables |  |  | TL 2 Deliverables |  |  | TL 3 Deliverables | TL 4 Deliverables | TL 5 Deliverables | TL 6 Deliverables
Date Due: 09/30 |  |  | Date Due: 10/09 |  |  | Date Due: 10/14 | Date Due: 10/28 & 10/30 | Date Due: 11/06 | Date Due: 11/13
By Monday : Initial Readme File in GIT | [6 empty] | By Monday 10/27:
[7 empty] | 1. Fully update your sections of the Gantt chart | 1: Update the gantt for what you have worked on.
2: Send me an update on what you have been working on this week.
By Wednesday 10/29:
1. Look over the coding standards in the GIT
2. Try to update your code to comply with the coding standards (to the best of your ability, BC is not expecting it to be perfect). Message me when you're done and I'll check you off.
Get deliverables to TL by 6pm on Date Due
Deliverable Tracker
| Aiden | Ro | Jaskaran | Safal | Syed | Gurneet
TL 1
TL 2 |  | ü
TL 3
TL 4 |  |  |  | ü
TL 5
TL 6

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 4 | 2 | 2 | 2 | 2 | 2 | 6 | 1 | 8
Aiden | 21 | ü | ü | ü | ü | ü | ü | ü | ü
Ro | 9 | ü | ü |  | ü | ü
Jaskaran | 11 | ü | ü | ü | ü |  | ü
Safal | 15 | ü | ü | ü | ü | ü | ü | ü
Syed | 9 | ü | ü | ü | ü
Gurneet | 9 | ü | ü | ü | ü
Total | 74 | 6 | 24 | 10 | 12 | 6 | 6 | 4 | 6 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Anne | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6 | bar: 7 to 11
| Chapter 1 and 2, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 13
Bill | Individual schedule | 2 | 3 | bar: 1 to 2
| Champion | 5 | 2 | bar: 7 to 11
| Chapter 3 and 4, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 10
Chris | Individual schedule | 1 | 1 | bar: 1
| Champion | 5 | 8 | bar: 2 to 6
| Merge schedules on google docs | 2 | 2 | bar: 7 to 8
| Standardize formating | 1 | 1 | bar: 9
| Assemble SA Powerpoint | 2 | 3 | bar: 10 to 11
| Subtotal | 11 | 15
Dan | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Chapter 5 and 6, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 11
Eric | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 1-3 | 4 | 3 | bar: 3 to 6
| Subtotal | 11 | 9
Fran | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 4-6 | 4 | 7 | bar: 3 to 6
| Subtotal | 11 | 13
| Total | 44 | 51
red is dependent on others

## Overhead
| Anne | Bill | Chris | Dan | Eric | Fran
Training | 10 | 6 | 27 | 9 | 9 | 9
SA Preesentation Prep | 2 | 3 | 1 | 6 | 6 | 6
Software Specialist Presnetaion Prep | 1 | 2 | 2 | 1 | 1 | 1
Team Lead Presentation Prep | 4 | 6 | 3 | 7 | 7 | 7
Oral Exam Prep | 8 | 3 | 9 | 11 | 11 | 11
Post Mortum Presentation Prep | 1 | 1 | 1 | 1 | 1 | 1
Total | 26 | 21 | 43 | 35 | 35 | 35